## Slide 1: GEF Project & Program Cycle & Key Policies GEF-7 National Dialogue

## Slide 2
GEF Partnership
GEF AGENCIES
ADB
AfDB
BOAD
CAF
CI
DBSA
EBRD
FECO
FUNBIO
IADB
IFAD
IUCN
FAO
UNDP
UNEP
UNIDO
WB
WWF-US
OFPs & PFPs
Convention FPs
Gov’t agencies
NGOs / CSOs
Private Sector
GEF COUNCIL
32 Constituencies
GEF ASSEMBLY
183 Countries
CONVENTIONS
CBD
UNFCCC
UNCCD
Stockholm(POPs)
Minamata
Guidance
Operations
Action
STAP
Independent Evaluation Office
GEF Trustee
GEF
Secretariat

## Slide 3: GEF Project Modalities
Full-Sized Project (FSP): financing over US$2M
Medium-Sized Project (MSP): financing of US$2 or less
Program: a longer term and strategic arrangement of individual yet interlinked projects that aim at achieving large-scale impacts on the global environment
Enabling Activity (EA): preparation of a plan, strategy or report to fulfill commitments under a Convention

## Slide 4: Full-Sized Project Cycle
Step 1
GEFSEC review
for PIF clearance
Step 2
Council approval
of PIF
Step 3
GEFSEC review
for CEO
endorsement
Agency:
project approval &
implementation,
Agency: project closing
& evaluation
STAP advisory
Agency:
project appraisal & CEO endorsement request
Trustee sets aside
GEF financing
(commits 40% Agency fee)
Trustee commits
GEF financing & 60% of Agency fee
Agency:
project concept
development & PIF submission
Agency:
PIR & Mid-term evaluation
Step 4
Terminal evaluation
/completion
report
In-country
project concept
identification
Notes: Start How project concepts are formulated; through national/local consultations; through Agency initiative
Step 1 Mention the PIF template and how to access; Importance of the OFP endorsement letter
Step 2 Cleared PIFs may not all be accommodated; It depends on resources availability, programming, etc.
Step 3 CEO Endorsement template – Project Document - Tracking Tools – Co-financing letters among others; take into consideration Council comments/STAP comments
Step 4 Lessons learned; best practices to feed to similar projects

## Slide 5: Medium-Sized Project Cycle (2 step approval)
Step 1
GEF CEO approval
Of PIF
Step 2
GEF CEO approval
Of Final MSP
Agency:
project approval &
implementation
Agency: project closing
& evaluation
Agency:
project appraisal & CEO approval request
Trustee sets aside
GEF financing
(commits 40% Agency fee)
Trustee commits
GEF financing & 60% of Agency fee
Agency:
project concept
development & PIF submission
Agency:
PIR & Mid-term evaluation
Step 3
Terminal evaluation
/completion
report
In-country
project concept
identification
Notes: Start How project concepts are formulated; through national/local consultations; through Agency initiative
Step 1 Mention the PIF template and how to access; Importance of the OFP endorsement letter
Step 2 Cleared PIFs may not all be accommodated; It depends on resources availability, programming, etc.
Step 3 CEO Endorsement template – Project Document - Tracking Tools – Co-financing letters among others; take into consideration Council comments/STAP comments
Step 4 Lessons learned; best practices to feed to similar projects

## Slide 6: Medium-Sized Project Cycle (1 step approval)
Step 1
GEF CEO approval
Of final MSP
Agency:
project implementation
Agency: project closing
& evaluation
Agency:
project appraisal & approval
Trustee commits
GEF financing & Agency fee
Agency:
project concept
development & Final MSP submission
Agency:
PIR & Mid-term evaluation
Step 3
Terminal evaluation
/completion
report
In-country
project concept
identification
Notes: Start How project concepts are formulated; through national/local consultations; through Agency initiative
Step 1 Mention the PIF template and how to access; Importance of the OFP endorsement letter
Step 2 Cleared PIFs may not all be accommodated; It depends on resources availability, programming, etc.
Step 3 CEO Endorsement template – Project Document - Tracking Tools – Co-financing letters among others; take into consideration Council comments/STAP comments
Step 4 Lessons learned; best practices to feed to similar projects

## Slide 7: Program
Step 1
GEFSEC review
for PFD clearance
Step 2
Council approval
of PFD
Step 3
GEFSEC review
Of PPG for
Child Project
Agency:
project approval &
implementation
Agency: project closing
& evaluation
STAP advisory
Agency:
project appraisal & CEO approval request
Trustee sets aside
GEF financing
(commits 40% Agency fee)
Trustee commits
GEF financing & 60% of Agency fee
Agency:
project concept
development & PIF submission
Agency:
PIR & Mid-term evaluation
Step 5
Terminal evaluation
/completion
report
In-country
project concept
identification
Step 4
GEF CEO approval
Of Child Project
Notes: Start How project concepts are formulated; through national/local consultations; through Agency initiative
Step 1 Mention the PIF template and how to access; Importance of the OFP endorsement letter
Step 2 Cleared PIFs may not all be accommodated; It depends on resources availability, programming, etc.
Step 3 CEO Endorsement template – Project Document - Tracking Tools – Co-financing letters among others; take into consideration Council comments/STAP comments
Step 4 Lessons learned; best practices to feed to similar projects

## Slide 8: Key GEF-7 Policies
Project identification | Concept submission (PIF/PFD) | Fully developed project (CEO approval/endorsement) | Implementation (PIF, MTR, TR)
Gender Equality Policy |  |  | 
Meaningful consultations w/ stakeholders on the proposed project/program, early screening | Indicative info on gender considerations & any measures to address these, including process to collect sex-disaggregated data & gender info | Gender analysis or equivalent socio-economic assessment that identifies and describes any gender differences, gender differentiated impacts & risks, and opportunities to address gender gaps and promote the empowerment of women, as relevant to the proposed activity Any corresponding gender-responsive measures to address differences, identified impacts & risks, and opportunities through a gender action plan or equivalent If gender-responsive measures have been identified, results framework or logical framework with actions, gender-sensitive indicators & sex-disaggregated targets | Annual reporting on, including through PIRs, mid-term reviews, and terminal evaluations on progress and results

## Slide 9
Project identification | Concept submission (PIF/PFD) |  | Fully developed project (CEO approval/endorsement) |  | Implementation (PIF, MTR, TR)
Stakeholder Engagement Policy |  |  |  |  | 
Meaningful consultations w/ stakeholders on the proposed project/program, early screening | Indicative info on stakeholder engagement, including any consultations conducted during project development, as well as information on how Stakeholders will be engaged in the project/ program, and means of engagement |  | Stakeholder engagement plans or equivalent, with stakeholders who have been and will be engaged, means of engagement, dissemination of information, roles and responsibilities, resource requirements, and timing throughout the project cycle |  | Annual reporting on, including through PIRs, mid-term reviews, and terminal evaluations on progress, challenges and outcomes
Environment & Social Safeguard Policy (in draft) |  |  |  |  | 
Meaningful consultations w/ stakeholders on the proposed project/program, early screening | Indicative info on any environmental and social risks and potential impacts associated with the proposed project/ program; and any measures to address these | Indicative info on any environmental and social risks and potential impacts associated with the proposed project/ program; and any measures to address these | Additional information on relevant risks and impacts, and measures to address these, including any assessments carried out, and any environmental and social management plans or the equivalent |  | Reporting at mid-term and completion on the implementation of relevant environmental and social management measures
Co-financing Policy |  |  |  |  | 
 | Indicative information on the expected amounts, sources and types of co-financing, and the sub-set of such co-financing that meets the definition of ”investment mobilized” |  | Confirmed information on the expected amounts, sources and types of co-financing and “investment mobilized”, with supporting evidence | Reporting at mid-term and completion on actual amounts, sources and types of co-financing and investment mobilized |